## Sheet1
Big Data Analytics Application Project Task List
Project Name |  | Measuring Community Friendliness of Programming Languages
Team Members |  | 1) Samarth Tambad
2) Rohit Nandwani
3)
Step | Task | Who | Start Date | End Date | Comments
Data Planning Stage
1 | Identify data sources | All | Mar 25 | Apr 3
2 | Plan where data will reside | All | Mar 25 | Apr 3 | •How much total data will be stored at any given time?
•Will the data fit in your Quickstart VM's HDFS, or do you need to use Dumbo? or the Cloud?
3 | Plan remediation action(s) | All | Mar 25 | Apr 10 | •What action will your application take in response to the insight discovered? Will it be automatic or does it require user action?
Data Cleaning and Profiling Stage (Each data source is owned by and processed by one team member - steps 4, 5, 6)
Data Source 1 Processing
4 | Write code to ingest data source 1 (if just a copy operation, please provide the command(s)) | Samarth | 6 April | _ | •In this step, you'll read the data from the source and write it or copy it into HDFS
5 | Write code to clean/format (ETL) data source 1 | Samarth | _ | _
6 | Write code to profile data source 1 | Samarth | _ | 13 April | •This is to characterize the data and the range of values in each column •You might notice unexpected values in a column - you may decide to normalize the values (e.g. Street vs. St. vs. street) in the ETL stage •Find min, max, and averages •Find min and max length of text fields
Data Source 2 Processing
4 | Write code to ingest data source 2 (if just a copy operation, please provide the command(s)) | Rohit | 6 April | _
5 | Write code to clean/format (ETL) data source 2 | Rohit | _ | _
6 | Write code to profile data source 2 | Rohit | _ | 13 April
Data Source 3 Processing
4 | Write code to ingest data source 3 (if just a copy operation, please provide the command(s)) | NA | NA | NA
5 | Write code to clean/format (ETL) data source 3 | NA | NA | NA
6 | Write code to profile data source 3 | NA | NA | NA
Data Source n Processing
4 | Write code to ingest data source n (if just a copy operation, please provide the command(s)) | NA | NA | NA
5 | Write code to clean/format (ETL) data source n | NA | NA | NA
6 | Write code to profile data source n | NA | NA | NA
Analytic and Application Development Stage
Develop UI / Visualization | Design the UI / Visualization | Rohit | 14 April | _
| Code the UI / Visualization | Rohit | _ | _
| Test the front-end UI / Visualization | Rohit | _ | 16 April
Develop Analytic | Design the back-end analytic | Samarth | 14 April | _
| Code the back-end analytic | Samarth | _ | _
| Test the back-end analytic code | Samarth | _ | _
| Analyze results produced by analytic | Samarth | _ | _ | • Test your hypothesis - does it hold? • Are the results what you expected? • Iterate to improve results, and/or to better understand results
| Iterate on the analytic | Samarth | _ | 20 April | • Iterate to improve results, and/or to better understand results • Do the results make sense? Are the results actionable?
Develop Application | Design the applicaton | Rohit | 17 April | _ | • How does the application talk to the analytic/analytic results? • How do the results get to the UI/Visualization?
| Code the applicaton | Rohit | _ | _
| Test the applicaton | Rohit | _ | 20 April
Final application code due |  | All | - | May. 3, 2020
© 2016-2020 Suzanne McIntosh, Cloudera